## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US01 | Create applicant profile | As a TA, I want to create and edit my applicant profile so that Module Organisers can view my contact details, education, skills and availability. | Must | 1 | 1. TA can enter name, student ID, email, programme, skills and availability. 2. Required fields are validated before save. 3. A saved profile can be reopened and edited later. | 3 SP | Core MVP; prerequisite for most TA actions. | 2026-03-08 | 2026-03-22
US02 | Upload CV | As a TA, I want to upload my CV so that my experience can be reviewed when I apply for a job. | Must | 1 | 1. TA can upload a PDF or DOC/DOCX file from the profile page. 2. The system stores the latest uploaded CV and shows the filename. 3. Invalid file types show a clear error message. | 3 SP | Core MVP; used by application review. | 2026-03-08 | 2026-03-22
US03 | Auto-fill profile from CV | As a TA, I want the system to extract key information from my CV so that I do not need to type everything manually. | Should | 2 | 1. After CV upload, the system extracts education, skills and experience text. 2. Extracted content pre-fills editable profile fields. 3. TA can review and modify extracted values before saving. | 5 SP | Prototype AI enhancement using simple parsing/extraction. | 2026-03-23 | 2026-04-12
US04 | Browse, search and filter jobs | As a TA, I want to browse and filter available TA and invigilation jobs so that I can quickly find suitable opportunities. | Must | 1 | 1. The job list shows title, module/activity, required skills, schedule and deadline. 2. TA can search by keyword and filter by module/activity, time or skills. 3. Closed or expired jobs are not shown in the open-jobs list. | 5 SP | Core + simple extension (search/filter). | 2026-03-08 | 2026-03-22
US05 | Save job for later | As a TA, I want to bookmark interesting jobs so that I can compare them and apply later. | Could | 3 | 1. TA can save or unsave a job from the job list or detail page. 2. Saved jobs appear in a separate list on the TA dashboard. 3. Saved status persists when the TA returns to the system. | 2 SP | Low-complexity usability enhancement. | 2026-04-13 | 2026-05-03
US06 | Apply for a job | As a TA, I want to submit an application for a selected job so that an MO can review me for the role. | Must | 1 | 1. TA can submit an application from the job detail page. 2. The current profile and uploaded CV are linked to the application. 3. A successful submission creates an application with status 'Submitted'. | 5 SP | Core MVP recruitment flow. | 2026-03-08 | 2026-03-22
US07 | View application status timeline | As a TA, I want to view the status and timeline of each application so that I know what stage it is in. | Must | 2 | 1. Each application shows a current status such as Submitted, In Review, Shortlisted, Accepted or Rejected. 2. The timeline is shown in chronological order. 3. The latest update date is visible to the TA. | 3 SP | Core status check + suggested timeline extension. | 2026-03-23 | 2026-04-12
US08 | Post job | As an MO, I want to create and publish a job so that suitable TAs can apply for it. | Must | 1 | 1. MO can enter title, module/activity type, description, requirements, hours, schedule and deadline. 2. Required fields must be completed before publish. 3. Published jobs become visible in the TA job list. | 5 SP | Core MVP for MO role. | 2026-03-08 | 2026-03-22
US09 | Review applicants for a job | As an MO, I want to view all applicants for one job in a single list so that I can compare candidates efficiently. | Must | 2 | 1. The applicant list shows applicant name, core skills, current status and current workload. 2. MO can open an applicant profile and CV from the list. 3. The list can be sorted by status or match score. | 5 SP | Depends on posting jobs and receiving applications. | 2026-03-23 | 2026-04-12
US10 | See candidate match score and missing skills | As an MO, I want to see a skill match score and missing-skill notes for each applicant so that I can shortlist faster. | Should | 2 | 1. The system calculates a visible match score from job requirements and applicant profile/CV data. 2. Missing skills are listed in plain language. 3. Score and notes appear beside each applicant in the review view. | 5 SP | AI feature combining skill matching and gap identification. | 2026-03-23 | 2026-04-12
US11 | Select or reject applicants | As an MO, I want to update application outcomes so that recruitment decisions are recorded and shared with TAs. | Must | 2 | 1. MO can change an application to Shortlisted, Accepted or Rejected. 2. Rejected applications can include an optional feedback reason. 3. The updated status becomes visible in the TA status view. | 5 SP | Core selection workflow. | 2026-03-23 | 2026-04-12
US12 | View TA overall workload | As an admin, I want to see each TA's total assigned work so that I can avoid over-allocation across jobs. | Must | 3 | 1. The dashboard shows each TA, assigned jobs and total assigned hours. 2. Admin can search for a TA and view the current workload summary. 3. The workload view updates after applicant selection. | 5 SP | Core admin requirement. | 2026-04-13 | 2026-05-03
US13 | Detect schedule conflict or overload | As an admin, I want the system to flag schedule clashes or excessive hours so that I can prevent unfair assignments. | Should | 3 | 1. The system flags overlapping schedules or hours above a defined threshold. 2. Warnings are visible on the admin workload view. 3. Each warning includes a short reason, such as 'time clash' or 'hour limit exceeded'. | 3 SP | Suggested extension; pairs with workload dashboard. | 2026-04-13 | 2026-05-03
US14 | Recommend lower-load suitable TAs | As an admin, I want the system to suggest suitable TAs with lighter workloads so that work can be distributed more fairly. | Could | 4 | 1. Recommendations consider required skills and current workload. 2. Each suggestion includes a short explanation for why the TA was recommended. 3. Admin can view suggestions before confirming assignment decisions. | 5 SP | AI balancing feature; useful for later iteration. | 2026-05-04 | 2026-05-24
US15 | Receive notifications and reminders | As a TA or MO, I want to receive simple notifications about application changes and deadlines so that I do not miss important actions. | Could | 4 | 1. TA is notified when an application status changes. 2. MO is notified when a new application is submitted. 3. Upcoming job deadlines can be shown as reminders on the dashboard. | 3 SP | Nice-to-have polish for final iteration. | 2026-05-04 | 2026-05-24